A Sprint fixed period or duration in which a team works to complete a set of tasks

An Epic is a big task or project that is too large to complete in one sprint. It is broken down into smaller tasks (stories) that can be completed over multiple sprints.

A Story is a small task . It is part of an Epic.

A Story Point is a number that represents how much effort a story takes to complete. (usually in form of Fibonacci series)

- Very Easy task

- Normal task

- Moderate task

- Difficult task

Storypoint -5 (1,2,3,5)

Sprint 1

Data Preparation (Epic 1)

Preparing Student Spreadsheet (USN1) 2

Creating Student Information Table (USN2) 3

Data Import (Epic 2)

Loading Data into Import Set Table (USN3) 2

Creating Transform Map and Field Mapping (USN4) 3

Total Story Point in Sprint 1= 2+3+2+3=10

Sprint 2

Data Transformation (Epic 3)

Running Transform and Verifying Results (USN5) 2

Reporting (Epic 4)

Creating Pie Chart Report (USN6) 3

Dashboard (Epic 5)

Developing Dashboard (USN7) 3

Total story Point in Sprint 2= 2+3+3=8

Total Story Points

Sprint 1 = 10

Sprint 2 = 8

Velocity= Total Story Points Completed​/ Number of Sprints

Total story Points= 10+8=18

No of Sprints= 2

Velocity =18/2

9(Story Points per Sprint)

Your team’s velocity is 9 Story Points per Sprint